## Overall Bug Score
Iteration | Task | Test (Number of tests) | Low Impact Bugs | High Impact Bugs | Critical Bugs | Score | Actions Taken
2 | Analysis - Doctor | 3 | 2 | 1 | - | 7 | Fix during buffer time
| Analysis - Referral | 3 | 1 | 2 | - | 11 | Fix during planned debugging time
| Analysis - Specialty | 3 | 1 | - | - | 1 | Fix during buffer time
| KPI - Medical | 2 | - | 1 | - | 5 | Fix during buffer time
| Gender & Age Report | 1 | - | 1 | - | 5 | Fix during buffer time
| Client - Create | 2 | 2 | - | - | 2 | Fix during buffer time
| Screening - CRUD | 6 | 4 | 1 | - | 9 | Fix during buffer time
| Total Score for Iteration 2 |  |  |  |  | 31 | Stop current development and resolve bugs

## Bug Log
S/N | Iter. | Function | Test No | Expected Result | Issues / Differing Result | Severity | Points | Status | Date Discovered | Date resolved | Remarks
1 | 2 | Analysis - Doctor | 1 | System should show result | No output | Low | 1 | solved | 2016-10-30 | 2016-10-31
2 | 2 | Analysis - Doctor | 2 | System should show result | Wrong Output | High | 5 | solved | 2016-10-30 | 2016-10-31
3 | 2 | Analysis - Doctor | 3 | System should show result | No output | Low | 1 | solved | 2016-10-30 | 2016-10-31
4 | 2 | Analysis - Referral | 1 | System should show result | Wrong Output | High | 5 | solved | 2016-10-30 | 2016-10-31
5 | 2 | Analysis - Referral | 2 | System should show result | Wrong Output | High | 5 | solved | 2016-10-30 | 2016-10-31
6 | 2 | Analysis - Referral | 3 | System should show result | No output | Low | 1 | solved | 2016-10-30 | 2016-10-31
7 | 2 | Analysis - Specialty | 1 | System should show result | No output | Low | 1 | solved | 2016-10-30 | 2016-10-31
8 | 2 | KPI - Medical | 1 | System should show result | Wrong Output | High | 5 | solved | 2016-10-30 | 2016-10-31
9 | 2 | Gender and Age | 1 | System should show result | Wrong Output | High | 5 | solved | 2016-10-30 | 2016-10-31
10 | 2 | Client - Create | 1 | System should show success result | No output | Low | 1 | unsolve | 2016-10-30
11 | 2 | Client - Create | 2 | System should show success result | No output | Low | 1 | unsolve | 2016-10-30
12 | 2 | Screening - CRUD | 1 | System should show success result / redirect back to screening page | No output | Low | 1 | unsolve | 2016-10-30
13 | 2 | Screening - CRUD | 2 | System should show success result / redirect back to screening page | No output | Low | 1 | unsolve | 2016-10-30
14 | 2 | Screening - CRUD | 3 | System should show success result / redirect back to screening page | No output | Low | 1 | unsolve | 2016-10-30
15 | 2 | Screening - CRUD | 4 | System should show success result / redirect back to screening page | No output | Low | 1 | unsolve | 2016-10-30
16 | 2 | Screening - CRUD | 5 | System should show success result / redirect back to screening page | Unable to edit any screenings | High | 5 | unsolve | 2016-10-30