## Slide 1
Proposal Submission
17 Oct
Acceptance
4 Nov
4 Oct
18 Oct
1 Nov
15 Nov
29 Nov
10
11
14
12
1
2
3
4
5
6
7
8
9
13 Dec
27 Dec
10 Jan
24 Jan
7 Feb
21 Feb
6 Mar
13
15
20 Mar
3 Apr
17 Apr
Midterm
27 Feb
Poster
27 Mar
Final
10 Apr
User Testing 1
28 Oct
User Testing 2
10 Jan
User Testing 4
17 Mar
Core
Secondary
Tertiary
Non-coding tasks
User Testing
Milestones
2 weeks iteration
Legend:
Iteration 1
Draft Proposal
Set up GitHub
Gather requirements
Prototype
Iteration 3
User Login/ Logout Account Management (Reset Password) Create/ Delete account by administrator
Iteration 5
Winter break
Iteration 11
Export Export dashboard/ performance reports for reporting purposes in PDF Format
Iteration 9
Email Notification Text Editor Edit email with preview & data from database Send email to Ulink staffs based on selected patients
Iteration 4
Exam Period
Iteration 8
Report - KPI Filter criteria and period (Visa/ Medical Team) Display infographic Show changes from previous month/year
Report - Ranking Filter criteria and period (Doctors/Specialty/Referral) Display ranking
Reports - Gender and Age Display infographic of Gender and Age breakdown
Iteration 10
Dashboard Summary and overview of latest reports Visa and Medical patients for the past 12 months Common types of visas requested List of clients who visited the past month Top 3 Doctors Top 5 Referral Sources
Preparation UT 3 and Midterm
Iteration 2
Analysis KPI of different teams Ranking (Doctor, Specialty, Referral) Gender and Age Report
Timeline Cradle to grave timeline Add/ Edit/ Delete Screenings Group patients for recommended screenings based on age
Clients (Patients) Create records View records Update records Delete records
Preparation for Acceptance
Iteration 12
Improve UI Bug Fixing
Preparation UT 4 and Final
Iteration 13
Improve UI Bug Fixing
Preparation for Final
Iteration 7
Data Management Upload excel file (client data) exported from Zoho CRM Add on to existing database Display clients’ list Search client Sort clients Client Profile - Basic information - Recommended screenings - Appointment & admission information
Preparation UT2
Go Live
15 Feb
Updated 14 Jan
Iteration 14
Preparation for Final
User Testing 3
10 Feb
Iteration 6
Screenings Create Screening View Screenings Update Screening Delete Screening Sort Screenings (gender, age range) Search Screening Group patients by recommended screening
Research for recommended screenings

## Slide 2
Proposal Submission
17 Oct
Acceptance
4 Nov
4 Oct
18 Oct
1 Nov
15 Nov
29 Nov
10
11
14
12
1
2
3
4
5
6
7
8
9
13 Dec
27 Dec
10 Jan
24 Jan
7 Feb
21 Feb
6 Mar
13
15
20 Mar
3 Apr
17 Apr
Midterm
20 Feb
Poster
27 Mar
Final
10 Apr
User Testing 1
28 Oct
User Testing 2
10 Jan
User Testing 4
17 Mar
Core
Secondary
Tertiary
Non-coding tasks
User Testing
Milestones
2 weeks iteration
Legend:
Iteration 1
Draft Proposal
Set up GitHub
Gather requirements
Prototype
Iteration 3
User Login/ Logout Account Management (Reset Password) Create/ Delete account by administrator
Iteration 5
Winter break
Iteration 11
Dashboard Summary and overview of latest analysis Visa and Medical patients for the past 6 months Common types of visa requested List of clients who visited the past month Top 3 Doctors engaged
Iteration 9
Analysis infographic - Gender and Age Display infographic of Gender and Age breakdown
Templates Upload email template for screening Reminder
Email Notification Choose email from existing templates Edit email with preview & data from database Send email to Ulink’s staff based on selected patients
Iteration 4
Exam Period
Iteration 8
Analysis infographic - KPI Filter criteria and period (Visa/ Medical Team) Display analysis infographic Show changes from previous month/year
Analysis - Ranking Filter criteria and period (Doctors/Specialty/Referral) Display ranking
Preparation UT2
Iteration 10
Search function Search for specific information in the entire application
Export Export analysis reports for reporting purposes
Preparation UT 3 and Midterm
Iteration 2
Analysis KPI of different teams Ranking (Doctor, Specialty, Referral) Gender and Age Report
Timeline Cradle to grave timeline Add/ Edit/ Delete Screenings Group patients for recommended screenings based on age
Clients (Patients) Create records View records Update records Delete records
Preparation for Acceptance
Iteration 12
Improve UI Bug Fixing
Preparation UT 4 and Final
Iteration 13
Improve UI Bug Fixing
Preparation for Final
Iteration 7
Data Management Upload excel file (patient data) exported from Zoho CRM Add on to existing database Display & Sorting from database Client Profile - Basic information - Recommended screenings Appointment & admission information
Go Live
15 Feb
Updated 3 Jan
Iteration 14
Preparation for Final
User Testing 3
10 Feb
Iteration 6
Screenings Create Screening View Screenings Update Screening Delete Screening Sort Screenings (demographics, age range) Group patients by age for recommended screenings
Research for recommended screenings

## Slide 3
Proposal Submission
17 Oct
Acceptance
4 Nov
4 Oct
18 Oct
1 Nov
15 Nov
29 Nov
10
11
14
12
1
2
3
4
5
6
7
8
9
13 Dec
27 Dec
10 Jan
24 Jan
7 Feb
21 Feb
6 Mar
13
15
20 Mar
3 Apr
17 Apr
Midterm
20 Feb
Poster
27 Mar
Final
10 Apr
User Testing 1
28 Oct
User Testing 2
10 Jan
User Testing 4
17 Mar
Core
Secondary
Tertiary
Non-coding tasks
User Testing
Milestones
2 weeks iteration
Legend:
Iteration 1
Draft Proposal
Set up GitHub
Gather requirements
Prototype
Iteration 3
User Login/ Logout Account Management Create/ Delete account by administrator
Iteration 5
Bootstrap function Upload excel file (patient data) exported from Zoho CRM Overwrite existing database
Screenings Create Screening View Screenings Update Screening Delete Screening Sort Screenings (demographics, age range) Group patients by age for recommended screenings
Research for recommended screenings
Iteration 10
Dashboard Summary and overview of latest analysis Visa and Medical patients for the past 6 months Common types of visa requested, List of clients who visited the past month Top 3 Doctors engaged
Preparation UT 3 and Midterm
Iteration 8
Analysis - Gender and Age Display infographic of Gender and Age breakdown
Templates Upload email template for screening Reminder
Email Notification Choose email from existing templates Edit email with preview & data from database Send email to Ulink’s staff based on selected patients
Iteration 11
Improve UI Bug Fixing
Preparation for Final
Iteration 4
Exam Period
Iteration 7
Analysis - Ranking Filter criteria and period (Doctors/Specialty/Referral) Display ranking
Analysis - KPI Filter criteria and period (Visa/ Medical Team) Display analysis infographic Show changes from previous month/year
Preparation UT2
Iteration 9
Search function Search for specific information in the entire application
Export Export analysis reports for reporting purposes
Iteration 2
Analysis KPI of different teams Ranking (Doctor, Specialty, Referral) Gender and Age Report
Timeline Cradle to grave timeline Add/ Edit/ Delete Screenings Group patients for recommended screenings based on age
Clients (Patients) Create records View records Update records Delete records
Preparation for Acceptance
Iteration 12
Improve UI Bug Fixing
Preparation UT 4 and Final
Iteration 13
Improve UI Bug Fixing
Preparation for Final
Iteration 6
Client Sorting of different columns View list (Filter by Visa/ Medical) Client Profile (Basic information and possible illnesses/screenings recommendations) Display appointments and admissions
Go Live
15 Feb
Updated 1 December
Iteration 14
Preparation for Final
User Testing 3
10 Feb

## Slide 4
Proposal Submission
17 Oct
Acceptance
4 Nov
4 Oct
18 Oct
1 Nov
15 Nov
29 Nov
10
11
14
12
1
2
3
4
5
6
7
8
9
13 Dec
27 Dec
10 Jan
24 Jan
7 Feb
21 Feb
6 Mar
13
15
20 Mar
3 Apr
17 Apr
Midterm
20 Feb
Poster
27 Mar
Final
10 Apr
User Testing 1
28 Oct
User Testing 2
10 Jan
User Testing 4
17 Mar
Core
Secondary
Tertiary
Non-coding tasks
User Testing
Milestones
2 weeks iteration
Legend:
Iteration 1
Draft Proposal
Set up GitHub
Gather requirements
Prototype
Iteration 3
User Login/ Logout Account Management
Iteration 5
Bootstrap function Upload excel file (patient data) exported from Zoho CRM Overwrite existing database
Screenings Create Screening View Screenings Update Screening Delete Screening Sort Screenings (demographics, age range)
Iteration 10
Dashboard Overview of latest analysis
Preparation UT 3 and Midterm
Iteration 8
Analysis - Gender and Age Display infographic of Gender and Age breakdown
Templates Upload email template for screening Reminder
Email Notification Choose email from existing templates Edit email with preview & data from database Send email to Ulink’s staff based on selected patients
Iteration 11
Improve UI Bug Fixing
Preparation for Final
Iteration 4
Exam Period
Iteration 7
Analysis - Ranking Filter criteria and period (Doctors/Specialty/Referral) Display ranking
Analysis - KPI Filter criteria and period (Visa/ Medical Team) Display analysis infographic Show changes from previous month/year
Preparation UT2
Iteration 9
Search function Search for specific information in the entire application
Export Export analysis reports for reporting purposes
Iteration 2
Analysis KPI of different teams Ranking (Doctor, Specialty, Referral) Gender and Age Report
Timeline Cradle to grave timeline Add/ Edit/ Delete Screenings Group patients for recommended screenings based on age
Clients (Patients) Create records View records Update records Delete records
Preparation for Acceptance
Iteration 12
Improve UI Bug Fixing
Preparation UT 4 and Final
Iteration 13
Improve UI Bug Fixing
Preparation for Final
Iteration 6
Timeline (Personalised Follow up) Display timeline with screenings Group patients by age for recommended screenings Send email of selected patients
Client Sorting of different columns View list (Filter by Visa/ Medical) Client Profile (Basic information and top 5 possible illness)
Go Live
15 Feb
Updated 1 December
Iteration 14
Preparation for Final
User Testing 3
10 Feb

## Slide 5
Proposal Submission
17 Oct
Acceptance
4 Nov
4 Oct
18 Oct
1 Nov
15 Nov
29 Nov
10
11
14
12
1
2
3
4
5
6
7
8
9
13 Dec
27 Dec
10 Jan
24 Jan
7 Feb
21 Feb
6 Mar
13
15
20 Mar
3 Apr
17 Apr
Midterm
20 Feb
Poster
27 Mar
Final
10 Apr
User Testing 1
28 Oct
User Testing 2
3 Feb
User Testing 3
17 Mar
Core
Secondary
Tertiary
Good-to-have
Non-coding tasks
User Testing
Milestones
2 weeks iteration
Legend:
Iteration 1
Draft Proposal
Set up GitHub
Gather requirements
Prototype
Iteration 3
User Login/ Logout Account Management
Services Create services & price list View list Update prices Delete records
Iteration 5
Doctors Create records View records Update records Delete records
Rules Customisation of rules for notifications
Revamp UI Improve UI Graphic representation of analysis results
Iteration 10
Migration of data from client’s current system
Preparation UT 2 and Midterm
Iteration 8
Invoices Generate invoice Export in PDF/ Excel Track deleted records
Report Generate reports (summary of price/ services/ admission) Filter function (patient, task, period)
Iteration 11
Create additional modules/ tabs Allow users to shift/ create new tabs
Currency Conversion Conversion of currency for invoice Link to Fixer.io
Iteration 4
Exam Period
Iteration 7
Template Upload email template Upload Letter of Guarantee/US Embassy Summary Screening Reminder
Email Notification Send email based on rules created Export PDF/ Word
SMS Notification Send appointment reminder to patients
Iteration 9
Fields Customisation Allow users to customise fields for forms
Search function Search for specific information in the entire application
Iteration 2
Analysis KPI of different teams Ranking (Doctor, Specialty, Referral) Gender and Age Report
Timeline Cradle to grave timeline Add/ Edit/ Delete Screenings Group patients for recommended screenings based on age
Clients (Patients) Create records View records Update records Delete records
Preparation for Acceptance
Iteration 12
Improve UI Bug Fixing
Preparation for Final
Iteration 13
Improve UI Bug Fixing
Preparation for Final
Iteration 6
Tasks Create tasks View tasks (dashboard)
Case CRUD Consultation CRUD Medical CRUD Admission CRUD Letter Of Guarantee
Revamp UI
Go Live
15 Feb
Acceptance
Iteration 14
Preparation for Final

## Slide 6
4 Oct
18 Oct
1 Nov
15 Nov
29 Nov
Proposal Submission
17 Oct
Acceptance
4 Nov
10
11
14
12
1
2
3
4
5
6
7
8
9
13 Dec
27 Dec
10 Jan
24 Jan
7 Feb
21 Feb
6 Mar
13
15
20 Mar
3 Apr
17 Apr
Midterm
20 Feb
Poster
27 Mar
Final
10 Apr
User Testing 1
28 Oct
User Testing 2
10 Feb
User Testing 3
17 Mar
Core
Secondary
Tertiary
Good-to-have
Non-coding tasks
User Testing
Milestones
2 weeks iteration
Legend:
Go Live
15 Feb

## Slide 7
View our deployed application here!