## Overall Bug Score
Iteration | Task | Test (Number of tests) | Low Impact Bugs | High Impact Bugs | Critical Bugs | Score | Actions Taken
|  |  | 1 | 5 | 10
2 | Analysis - Doctor | 3 | 0 | 0 | 0 | 0 | -
| Analysis - Referral | 3 | 0 | 0 | 0 | 0 | -
| Analysis - Specialty | 3 | 0 | 0 | 0 | 0 | -
| KPI - VISA | 3 |  |  |  |  | -
| KPI - Medical | 2 | 0 |  | 0 | 0 | -
| Gender & Age Report | 1 | 0 |  | 0 | 0 | -
| Client - CRUD | 3 | 0 | 1 | 0 | 5 | Fix during buffer time
| Screening - CRUD | 6 |  | 1 | 0 | 5 | Fix during buffer time
| Total Score for Iteration 2 |  |  |  |  | 10 | Fix during buffer time
3 | Login | 12 | - | 3 | - | 15 | Use planned debugging time during iteration
| Account Management | 8 | 4 | 1 | - | 9 | Fix during buffer time
| Protect | 7 | - | 3 | - | 15 | Use planned debugging time during iteration
| Total Score for Iteration 3 |  |  |  |  | 39

## Bug Log
S/N | Iter. | Function | Test No | Expected Result | Issues / Differing Result | Severity | Points | Status | Date Discovered | Date resolved | Remarks
1 | 2 | Client - Edit | 2 | System should show the updated info for client | Unable to edit any client | High | 5 | unsolve | 2016-10-30 | - | Function dropped
2 | 2 | Screening - Edit | 5 | System should show the updated info for screening | Unable to edit any screenings | High | 5 | unsolve | 2016-10-30 | - | Pushed to future iteration due to rescope
3 | 3 | Login & Account Management - login | 1,5,8 | Error Message Shown for wrong credentials | No error message, not sure is UI not display properly or codes did not do validation for wrong credentials | High | 5
4 | 3 | Login & Account Management -acct | 7 | Account created or related message should show | No such message, page did not redirect | Low | 1
5 | 3 | Login & Account Management -acct | 11,22 | Able to change user/admin's password | Page did not redirect to anywhere to update password | High | 5
6 | 3 | Login & Account Management - login | 12 | Error Message Shown for wrong credentials | able to login with old password, related to test no 11 | High | 5
7 | 3 | Login & Account Management - login | 13 | Redirect to homepage | Did not redirect to home page, related to test no 11 | High | 5
8 | 3 | Login & Account Management -acct | 14 | Account deleted or related message should show | Did not show success message, page did not redirect / refresh. Have to manually refresh to see it work. | Low | 1
9 | 3 | Login & Account Management -acct | 15,16 | Account created or related message should show | Did not show success message, page did not redirect / refresh. Have to manually go to acct management page to see it work. | Low | 1
10 | 3 | Login & Account Management -protect | 18,27 | Normal user should not able to access the page | Can access the page | High | 5
11 | 3 | Login & Account Management -protect | 19 | Normal user should not have the acct management tab in their header | Normal user can view it on the header and can access it | High | 5
12 | 3 | Login & Account Management -acct | 20, 21 | Error Message shown for account existed | No error message. Unsure if the new account overwrites the existing account - checked DB, it did not. | Low | 1
13 | 3 | Login & Account Management -protect | 23,24,25,26 | Unable to access the page without login | Able to access | High | 5

## Mitigation Plan
0 | Fix during buffer time
11 | Use planned debugging time in the iteration
21 | Stop current development immediately and resolve bugs. PM to reschedule the project