## Overall Bug Score
Iteration | Task | Test (Number of tests) | Low Impact Bugs | High Impact Bugs | Critical Bugs | Score | Actions Taken
|  |  | 1 | 5 | 10
2 | Analysis - Doctor | 3 | 0 | 0 | 0 | 0 | -
| Analysis - Referral | 3 | 0 | 0 | 0 | 0 | -
| Analysis - Specialty | 3 | 0 | 0 | 0 | 0 | -
| KPI - VISA | 3 |  |  |  |  | -
| KPI - Medical | 2 | 0 |  | 0 | 0 | -
| Gender & Age Report | 1 | 0 |  | 0 | 0 | -
| Client - CRUD | 3 | 0 | 1 | 0 | 5 | Fix during buffer time
| Screening - CRUD | 6 |  | 1 | 0 | 5 | Fix during buffer time
| Total Score for Iteration 2 |  |  |  |  | 10 | Fix during buffer time
3 | Login | 12 | - | 3 | - | 15 | Use planned debugging time during iteration
| Account Management | 8 | 4 | 1 | - | 9 | Fix during buffer time
| Protect | 7 | - | 3 | - | 15 | Use planned debugging time during iteration
| Total Score for Iteration 3 |  |  |  |  | 39
6 | Screenings | 15 | 4 | 3 |  | 19 | Use planned debugging time during iteration
| Total Score for Iteration 6 |  |  |  |  | 19

## Bug Log
S/N | Iter. | Function | Test No | Expected Result | Issues / Differing Result | Severity | Points | Status | Date Discovered | Date resolved | Remarks
1 | 2 | Client - Edit | 2 | System should show the updated info for client | Unable to edit any client | High | 5 | unsolve | 2016-10-30 | - | Function dropped
2 | 2 | Screening - Edit | 5 | System should show the updated info for screening | Unable to edit any screenings | High | 5 | unsolve | 2016-10-30 | - | Pushed to future iteration due to rescope
3 | 3 | Login & Account Management - login | 1,5,8 | Error Message Shown for wrong credentials | No error message, not sure is UI not display properly or codes did not do validation for wrong credentials | High | 5
4 | 3 | Login & Account Management -acct | 7 | Account created or related message should show | Success msg doesn’t show long enough and msg is red | Low | 1
5 | 3 | Login & Account Management -acct | 11,22 | Able to change user/admin's password | Page did not redirect to anywhere to update password | High | 5 | Solved |  | 2017-06-01
6 | 3 | Login & Account Management - login | 12 | Error Message Shown for wrong credentials | able to login with old password, related to test no 11 | High | 5 | Solved |  | 2017-06-01
7 | 3 | Login & Account Management - login | 13 | Redirect to homepage | Did not redirect to home page, related to test no 11 | High | 5 | ????
8 | 3 | Login & Account Management -acct | 14 | Account deleted or related message should show | Did not show success message | Low | 1
9 | 3 | Login & Account Management -acct | 15,16 | Account created or related message should show | page did not redirect / refresh. Have to manually go to acct management page to see it work. | Low | 1 | Solved
10 | 3 | Login & Account Management -protect | 18,27 | Normal user should not able to access the page | Can access the page | High | 5 | Solved
11 | 3 | Login & Account Management -protect | 19 | Normal user should not have the acct management tab in their header | Normal user can view it on the header and can access it | High | 5
12 | 3 | Login & Account Management -acct | 20, 21 | Error Message shown for account existed | No error message. Unsure if the new account overwrites the existing account - checked DB, it did not. | Low | 1
13 | 3 | Login & Account Management -protect | 23,24,25,26 | Unable to access the page without login | Able to access | High | 5 | Solved
14 | 6 | Screenings - C | 1,2,3,4 | Add Screenings | DB capture data not according to demographic | High | 5
15 | 6 | Screenings - R | 5,7,10 | Page should display the newly created screenings / updated screenings | Page did not display the screenings since db did not capture the data (screenings) | Low | 1 | Solved
16 | 6 | Screenings - U | 6 | Able to edit screening (edit those that created in test1,2,3,4) | Unable to edit the newly created screenings (related to test 1,2,3,4) | Low | 1
17 | 6 | Screenings - D | 8 | Able to click on the delete button, screening removed from db | Unable to click on the delete button for this screening as it did not appear (related to test 1,2,3,4) | Low | 1 | Solved
18 | 6 | Screenings | 9 | Infant's Age validation for add screening | No error message shown (UI) | Low | 1
19 | 6 | Screenings - Filter | 11,12,13 | Display screenings' details according to the filter | Displayed unrelated data | High | 5
20 | 6 | Screenings - Client List | 14,15 | View filtered screening's client list | Page did not redirect to view client list page | High | 5
|  | Added By KX |  | BUG description
|  | Login & Account Management |  | Clicking on "Edit" even when password is empty | Success msg is still shown BUT should display error msg
|  | Login & Account Management |  | login with new password | Cannot log in with new password
Username is taken displayed even though new
|  | Screenings |  | No success msg to show added screenings
Add female/male/infant only but all 3 come out
Empty field error msg shown at wrong field
|  | Edit screenings |  | Fields not autopopulated for screening
When all fields entered, old screening edit, new screening also created

## Mitigation Plan
0 | Fix during buffer time
11 | Use planned debugging time in the iteration
21 | Stop current development immediately and resolve bugs. PM to reschedule the project