## Overall Bug Score
Iteration | Task | Test (Number of tests) | Low Impact Bugs | High Impact Bugs | Critical Bugs | Score | Actions Taken
|  |  | 1 | 5 | 10
2 | Analysis - Doctor | 3 | 0 | 0 | 0 | 0 | -
| Analysis - Referral | 3 | 0 | 0 | 0 | 0 | -
| Analysis - Specialty | 3 | 0 | 0 | 0 | 0 | -
| KPI - VISA | 3 |  |  |  |  | -
| KPI - Medical | 2 | 0 |  | 0 | 0 | -
| Gender & Age Report | 1 | 0 |  | 0 | 0 | -
| Client - CRUD | 3 | 0 | 1 | 0 | 5 | Fix during buffer time
| Screening - CRUD | 6 |  | 1 | 0 | 5 | Fix during buffer time
| Total Score for Iteration 2 |  |  |  |  | 10 | Fix during buffer time
3 | Login | 12 | - | 3 | - | 15 | Use planned debugging time during iteration
| Account Management | 8 | 4 | 1 | - | 9 | Fix during buffer time
| Protect | 7 | - | 3 | - | 15 | Use planned debugging time during iteration
| Total Score for Iteration 3 |  |  |  |  | 39
6 | Screenings | 15 | 4 | 3 |  | 19 | Use planned debugging time during iteration
| Total Score for Iteration 6 |  |  |  |  | 19
8 | Report | 8 | 1 | 3 |  | 16 | Use planned debugging time during iteration
| Ranking | 10 | - | 2 |  | 10 | Fix during buffer time
| Total Score for Iteration 6 |  |  |  |  | 26

## Bug Log
S/N | Curr. Iter. | Func Iter. | Function | Test No | Expected Result | Issues / Differing Result | Severity | Points | Status | Date Discovered | Date resolved | Remarks
1 | 2 | 2 | Client - Edit | 2 | System should show the updated info for client | Unable to edit any client | High | 5 | unsolved | 2016-10-30 | - | Function dropped
2 | 2 | 2 | Screening - Edit | 5 | System should show the updated info for screening | Unable to edit any screenings | High | 5 | unsolved | 2016-10-30 | - | Pushed to future iteration due to rescope
3 | 3 | 3 | Login & Account Management - login | 1,5,8 | Error Message Shown for wrong credentials | No error message, not sure is UI not display properly or codes did not do validation for wrong credentials | High | 5 | solved
4 | 3 | 3 | Login & Account Management -acct | 7 | Account created or related message should show | Username is taken was shown instead of account created and it appeared for 1 second | Low | 1 | solved
5 | 3 | 3 | Login & Account Management -acct | 11,22 | Able to change user/admin's password | Page did not respond when clicking the reset button, browser then appear out of memory | High | 5 | solved | 2017-07-01
6 | 3 | 3 | Login & Account Management - login | 12 | Error Message Shown for wrong credentials | able to login with old password, ecf from test no 11 | High | 5 | solved | 2017-07-01
7 | 3 | 3 | Login & Account Management - login | 13 | Redirect to homepage | Unable to log in with the updated password, ecf from test no 11 | High | 5 | solved
8 | 3 | 3 | Login & Account Management -acct | 14 | Account deleted or related message should show | Did not show success message | Low | 1 | solved
9 | 3 | 3 | Login & Account Management -acct | 15,16 | Account created or related message should show | page did not redirect / refresh. Have to manually go to acct management page to see it work. | Low | 1 | solved | 2017-07-01
10 | 3 | 3 | Login & Account Management -protect | 18 | Normal user should not able to access the page | able to access the url and did not redirect to home page or show error message | High | 5 | kiv | 2017-07-01
11 | 3 | 3 | Login & Account Management -protect | 19 | Normal user should not have the acct management tab in their header | able to access the url and did not redirect to home page or show error message | High | 5 | kiv
12 | 3 | 3 | Login & Account Management -acct | 20, 21 | Error Message shown for account existed | Error message shown for one second but disappear after that. | Low | 1 | solved
13 | 3 | 3 | Login & Account Management -protect | 23,24,25,26 | Unable to access the page without login | Able to access | High | 5 | Solved
| 3 | 3 | Login & Account Management -acct | 27 | Normal user should not able to access the page | able to access edituserpassword and createaccount.html, tried to create an account and account created message shown but db did not capture it | High | 5 | kiv | 2017-07-01
14 | 3 | 3 | Login & Account Management - value validation | 28 | input empty fields should display when clicking the reset password | Nothing happens | Low | 1 | solved | 2017-08-01
15 | 6 | 6 | Screenings - C | 1,2,3,4 | Add Screenings | page refreshed when clicking the add button, but screenings was not added to db. | High | 5 | Solved
16 | 6 | 6 | Screenings - R | 7 | Success message should show to indicate screenings updated | no success message | Low | 1 | Solved
17 | 6 | 6 | Screenings - U | 6 | Able to edit screening (edit those that created in test1,2,3,4) | No screenings in the view screening page, unable to edit | Low | 1 | Solved
18 | 6 | 6 | Screenings - D | 8 | Able to click on the delete button, screening removed from db | Demograhics affected was updated wrongly | High | 5 | Solved | 2017-08-01
19 | 6 | 6 | Screenings - value specific validation | 10,11 | Infant's Age validation for add screening | No error message shown (UI), screenings was added | High | 5 | Solved
20 | 6 | 6 | Screenings - Filter |  | Able to filter screenings for infant between 0 to 2 years old | Filter missing | Low |  |  | 2017-08-01 |  | Feature dropped
21 | 6 | 6 | Screenings - Filter |  | Display screenings' details according to the filter | Filter missing | High |  |  |  |  | Feature dropped
22 | 6 | 6 | Screenings - Client List |  | View filtered screening's client list | Filter missing | High |  |  |  |  | Feature dropped
23 | 6 | 6 | Screenings - sort | 23-27 | Display result in a sorted order (asc - desc / desc - asc) | Unable to click on the header to sort | Low | 1 | Solved | 2017-08-01
24 | 6 | 6 | Screenings - value validation | 30 | Error message to show "input empty fields" | Filter missing, therefore unable to click on generate button | High | 5 | Solved | 2017-08-01
|  |  | Added By KX |  | BUG description
25 |  |  | Login & Account Management |  | Clicking on "Edit" even when password is empty | Success msg is still shown BUT should display error msg |  |  | solved
26 |  |  | Login & Account Management |  | login with new password | Cannot log in with new password |  |  | solved
27 | [5 empty] | Username is taken displayed even though new |  |  | solved
28 |  |  | Screenings |  | No success msg to show added screenings |  |  |  | solved
29 |  |  |  |  | Add female/male/infant only but all 3 come out |  |  |  | solved |  |  | Intended to be this way
30 |  |  |  |  | Empty field error msg shown at wrong field |  |  |  | solved
31 |  |  | Edit screenings |  | Fields not autopopulated for screening |  |  |  | solved
32 |  |  |  |  | When all fields entered, old screening edit, new screening also created |  |  |  | solved
33 | 7 | 7 | Upload - wrong file format | 1,2,3,4 | Error with file or related message should show, timestamp should not be updated | page redirect with no error / success message | Low | 1 | - |  |  | Requirements changed for bootstrap (extra column).Data file not suitable
34 | 7 | 7 | Upload - wrong header structure, file correct format | 5 | Wrong File format shown Content should not be found in database Timestamp should not be updated | page redirect with no error / success message | Hgh | 5 | -
35 | 7 | 7 | Upload - correct file format | 6 | "File successfully updated" shown 100 Records loaded into database Timestamp updated to current time | page redirect with no error / success message | High | 5 | -
36 | 7 | 7 | Upload - csv file | 7 | "Wrong File Format" shown Timestamp should not be updated to current time | page redirect with no error / success message | High | 5 | -
37 | 7 | 7 | Upload - correct file format | 8 | "File successfully updated" shown 300 Records loaded into database Timestamp updated to current time | page redirect with no error / success message | High | 5 | -
38 | 7 | 7 | Upload - correct file format | 9 | "File successfully updated" shown 400 Records loaded into database Timestamp updated to current time | page redirect with no error / success message | High | 5 | -
39 | 7 | 7 | Upload - correct file format | 10 | "File successfully updated" shown 1000 Records loaded into database Row 2003 - 2005 should not be found in database Timestamp updated to current time | page redirect with no error / success message | High | 5 | -
40 | 7 | 7 | Upload - correct file format | 11 | "File successfully updated" shown 700 Records loaded into database Row 703 - 705 should not be found in database Timestamp updated to current time | page redirect with no error / success message | High | 5 | -
41 | 7 | 7 | Upload - correct file format | not in testcase | Upload Testing2.1 "File successfully updated" shown 200 records loaded into db, timestamp updated to current time | page redirect with no error / success message | High | 5 | -
42 | 7 | 7 | Upload - correct file format, wrong header | 12 | Data not relevant or related message shown | page redirect with no error / success message |  |  | - |  | 2017-01-22
43 | 7 | 7 | Clients Page - Sort Client | 1 - 6 | Sort Clients in an order | No cients displayed | High | 5 | solved
44 | 7 | 7 | Client - Display Profile | 7,9 | Display Client's profile | Unable to click on client's name to view its profile | High | 5 | solved |  | 2017-01-22
45 | 7 | 7 | Client - Display Profile | 8,10 | View Client's appointments | Unable to view | High | 5 | solved |  | 2017-01-22
46 | 7 | 6 | Screenings - Add (Adults) | - | in viewScreeningsAdult.html, upon clicking 'add new screening' , it should redirect to addscreeningadult.html | direct to addscreening.html (for infant) | low |  | solved |  | 2017-01-22
47 | 7 | 6 | Screenings - Add (Infant) |  | Vaccination / Screening | Vaccination/ screening | low | 1
48 | 7 | 6 | Screenings - Link to Patient View |  | Should display male clients above 20 years old for Cancers | Returned Client A, C,D,E,F whose gender are either male / female / blank | High | 5 | solved
49 | 7 | 6 | Screenings - Link to Patient View |  | Should display infant for illness - pwqpqpw | Returned Client A, C,D,E,F, G whose age are above 6 | High | 5 | solved
50 | 7 | 6 | Screenings - sort adult |  |  | Gender = Male, the whole table shrink in size | High | 5 | solved |  | 2017-01-22
51 | 7 | 6 | Screenings - sort adult |  |  | After sorting gender = male, sort back to 'all', there is no change in result | High | 5 | solved |  | 2017-01-22
52 | 7 | 6 | Screenings - sort adult |  |  | After sorting gender = male, sort back to female and the table disappear, 'delete' was shown | High | 5 | solved |  | 2017-01-22
53 | 7 | 6 | Screenings - sort infant |  |  | when sorting the age, illness and screening for infant, the data for infant changes to adult's | High | 5 | solved |  | 2017-01-22
54 | 7 | 7 | Upload - timestamp |  |  | timestamp updated to current time, last three lines of the data file were also uploaded into database | High | 5 | solved
55 | 7 | 7 | Client List - drop down list |  | Table should show data based on the dropdown list | No change in table - data not sorted | High | 5 | solved |  | 2017-01-22
56 | 7 | 7 | View Client Info |  | Should show the various screenings for each client | No screenings shown in each client info | High | 5 | solved |  | 2017-01-22
57 | 7 |  | Seach Box in Navigator |  | Shouldn’t show in the header for all pages |  | High | 5 | solved |  | 2017-01-22
58 | 7 | 8 | Screenings - sort adult |  | gender = male , currently display both male and female | Gender = male , display screenings for male. | Low | 1 | solved | 2017-01-22
59 | 7 | 8 | Screenings - Sort Adullt (Result Sequence) |  | common illness and screening not sorted in correct order |  | High | 5 | solved | 2017-01-22
60 | 7 | 8 | Search in Screening |  | searched 'check' should appear screenings with 'check %' (linda's request) | displayed both 'check %' and '% check %' | High | 5 |  | 2017-01-22
61 | 7 | 8 | Search in client |  | searched 'di' should appear clients with 'di' as starting name (Linda's request) |  | High | 5 |  | 2017-01-22
62 | 7 | 8 | Report - KPI |  | No response when clicking the generatte results button | Should display result | High | 5 | solved | 2017-01-22 | 2017-02-08
63 | 9 | 8 | Upload / Bootstrap |  | 864 Records loaded | 0 Records loaded | High | 5 | solved |  | 2017-02-08
64 | 9 | 8 | Report - KPI (VISA) | 1,2,3,4 |  | No response when clicking the generated result button. Should display result | High | 5 | solved | 2017-02-06 | 2017-02-08
65 | 9 | 8 | Report - KPI (Medical) | 5,6,7,8 | Have numbers for inpatient and outpatient | No figures for outpatient. Refer to test case for the expected result. | High | 5 | solved | 2017-02-06
66 | 9 | 8 | Report - KPI (Medical) | 5,6,7,8 |  | Month in "Compare with PREVIOUS YEAR" is wrong | Low | 1 | solved | 2017-02-06
67 | 9 | 8 | Report - KPI (Medical) | 5,6,7,8 |  | % calculation is wrong (0% for all) | High | 5 | solved | 2017-02-06
68 | 9 | 8 | Ranking - View Doctor List | 5 | A total of 4 engagement by 2 doctors | multiple doctors shown, rank 1 has 9 engagement | High | 5 | solved | 2017-02-06
69 | 9 | 8 | Ranking - View Doctor List | 7 | Total 6 engegement by 4 doctors | a lot of doctor names are shown is wrong | High | 5 | solved | 2017-02-06
70 | 9 | 8 | Dashboard - types of visa requested | 1 |  | More than 1000 patients shown in graph (DB has 861 records / patients) | High | 5 | Solved | 2017-02-06
71 | 9 | 9 | Dashboard - VISA clients | 2 | Jul, aug,sept,oct,nov,dec as latest data in db is dec | Latest result is Dec, graph shows Jan - Jun | High | 5 | solved | 2017-02-06
72 | 9 | 9 | Dashboard - Medical Clients | 3 |  | Latest result is Dec, graph shows Jan - Jun | High | 5 | solved | 2017-02-06
73 | 9 | 9 | Dashboard - top 3 | 4 |  | Missing table | High | 5 | solved | 2017-02-06
74 | 9 | 9 | Dashboard - top 5 | 5 |  | Missing table | High | 5 | solved | 2017-02-06
75 | 9 | 9 | Gender Age Report | 1 to 9 |  | Female for all above 90% is wrong | High | 5 | solved | 2017-02-06
76 | 10 | 7 | Screenings - Infant (View client list) |  | Display only client age 0 - 2 for infant's screenings (age cap at 2 years old ) | displayed age up till 77 years old which is incorrect | High | 5 |  | 2017-02-08
77 | 10 | 7 | Screenings - sort (view - adult and infant) |  |  | illness and screenings are not sorted in asc or desc order | Low |  | kiv | 2017-02-08
78 | 1 | 7 | Screenings - filter by gender ( view - adult) |  | gender = male , then display screenings for Male only | male selected, displayed both male and female which is incorrect | High | 5 | solved | 2017-02-08
79 | 10 | 7 | Client - Search |  |  | search "Sin" in search box, client name 'Lena Mardinis" appear | High | 5 |  | 2017-02-08
80 | 10 | 8 | Report - KPI (Medica and Visa) | - |  | % sign missing in percentage increase / decrease | Low | 1 | solved | 2017-02-13
81 | 10 | 8 | Report - KPI (Medica and Visa) | - |  | Graph - inpatient and outpatient value is different from the table | High | 5 | solved | 2017-02-13
82 | 10 | 8 | Report Ranking |  |  | "Start Date before end date" error appear when start date was before end date. | Low | 1 | solved | 2017-02-13
83 | 10 | 8 | Report - ranking speciaty |  |  | click 'view doctor list' not responding | High | 5 | solved | 2017-02-13
84 | 10 | 9 | Gender-Age Report | 3,5,6,8 |  | some client's age increment by one (clients have yet to celebrate their birthday this year) | High | 5 | solved | 2017-02-13
85 | 10 | 9 | Dashboard - Total Visa Request | 1 |  | Results different. Some types of visa has 1 or 3 missing count | High | 5 | solved | 2017-02-13
86 | 10 | 9 | Dashboard - Top 5 Referred by | - |  | "Top 5 referred by " title missing | Low |  | solved | 2017-02-13
87 | 10 | 9 | Dashboard - Top 5 Referred by | - |  | This month & last month shown instead of dec and nov | Low | 1 | solved | 2017-02-13
88 | 10 | 9 | Dashboard - Top 5 Referred by | 5 |  | This month 's rank 4 missing | High | 5 | solved | 2017-02-13
89 | 10 | 9 | Dashboard - Top 3 Doctor | - |  | "This month" & "last month" shown instead of "dec" and "nov" | Low | 1 | solved | 2017-02-13
90 | 10 | 9 | Dashboard - Top 3 Doctor | - |  | "Top 3 Doctors" title missing | Low | 1 | solved | 2017-02-13
91 | 10 | 10 | View Screening - patient list |  |  | UI - screening name appear at the side of the table in view patient page | Low | 1 | solved | 2017-02-14
92 | 10 | 10 | Email function |  |  | bullet point not working / not printing out | Low | 1 | solved | 2017-02-14
93 | 10 | 10 | Email function |  |  | doube spacing not working / not printing out | Low | 1 |  | 2017-02-14
94 | 10 | 10 | Email function |  |  | special characters not working / not printing out, unable to save as template as well | Low | 1 | solved | 2017-02-14
95 | 10 | 10 | Email function |  |  | "1234567890" not working / not printing out | Low | 1 | solved | 2017-02-14
96 | 10 | 10 | Email function |  |  | right alignment not working / not printing out ("right" button) | Low | 1 | kiv | 2017-02-14
97 | 10 | 10 | Email function |  |  | font changed to smaller size, works. But changed font size or color or to another font , doesn't work / not printing out | Low | 1 | kiv | 2017-02-14
98 | 10 | 10 | Report - index |  |  | percentage displayed was 'x clients' (x refers to number of clients) , should convert x to % and then display % | High | 5 | solved | 2017-02-21
99 | 10 | 10 | Report - index |  |  | only one staffs displayed (there is 5 in db) | High | 5 | solved | 2017-02-21
100 | 11 | 9 | Dashboard - visa and medical clients |  |  | year missing | Low | 1 | KIV | 2017-02-21
101 | 11 | 9 | dashboard - top doctors / referral |  |  | upon clicking either buttons, caused some ui problem | Low | 1 | solved | 2017-02-21
102 | 11 | 7 | bootstrap |  |  | wrong content (same file format) shows success message eg. Test cases | High | 5 | solved | 2017-02-21
103 | 11 | 7 | bootstrap |  |  | missing column / extra column (same file format) shows success message with 0 rows updated. | Low | 1 | solved | 2017-02-21
104 | 11 | 7 | bootstrap |  |  | first row (header) removed, caused UI problem and also shows success message | Low | 1 | solved | 2017-02-21
105 | 11 | 8 | Report - KPI |  |  | months in graph - Earlier month on the left | Low | 1 | solved | 2017-02-21
106 | 11 | 8 | Report - KPI |  |  | % missing in Visa only | Low | 1 | solved | 2017-02-21
107 | 11 | 8 | Report - ranking speciaty |  |  | Table's header "speciality" (typo) | Low | 1 | solved | 2017-02-21
108 | 11 | 8 | Report - ranking speciaty |  |  | View doctor list (in table) not responding | High | 5 | solved | 2017-02-21
109 | 11 | 9 | Gender Age Report |  |  | total clients in the report is missing. | Low | 1 | KIV | 2017-02-21
110 | 11 | 11 | Email function - Text Editor |  |  | attached image function missing | Low | 1 |  | 2017-02-21
111 | 11 |  | bootstrap |  |  | missing cols / extra column but with correct file extension shows error msg: “wrong file extension…”, should show error message : wrong content | Low | 1 |  | 2017-03-01
112 | 11 |  | bootstrap |  |  | upload irrelevant data / first row missing but with correct file extension shows error message : "incorrect file selected", should show error message : wrong content | Low | 1 |  | 2017-03-01
113 | 11 |  | bootstrap |  |  | upload 3070 data (xlsx) causes service unavailable | High | 5 |  | 2017-03-01
114 | 11 |  | bootstrap |  |  | upload irrelevant content with either xls or xlsx also saves the time and display the failed bootstrap time as last bootstrap time. | Low | 1 |  | 2017-03-01
115 | 11 |  | Screening - Edit infant |  |  | currently redirect to adult page. Pls change redirect to infant screening (expected) | Low | 1 |  | 2017-03-01
116 | 11 |  | Screening - view patient in screening |  |  | Email sent date missing in screenings and client profile | Low | 1 |  | 2017-03-01
117 | 11 |  | Screening - search + select all button |  |  | Search for Lyn. Click on ‘select all’ button for PIC Lyn and send email (for example 2 clients selected), more than 2 clients were selected to send email. | Low | 1 |  | 2017-03-01
118 | 11 |  | Sreening |  |  | Change error message “Please select at least 1 checkbox” to “1 client” | Low | 1 |  | 2017-03-01
119 | 11 |  | Screening - Add |  |  | Copy and paste bold values / text not working in add screening | High | 5 |  | 2017-03-01
120 | 11 |  | Screening - sort patient list |  |  | Enable sorting for age, client Name, email sent date for this page. | High | 5 |  | 2017-03-01
121 | 11 |  | Report |  |  | No error message on ‘date not selected’ after clicking the generate button for all reports – ranking , index | Low | 1 |  | 2017-03-01
122 | 11 |  | Email |  |  | Long space in email template became ‘next line’ in email | Low | 1 |  | 2017-03-01
123 | 11 |  | Email |  |  | Need to include [PIC] tag for email template | Low | 1 |  | 2017-03-01
124 | 11 |  | Client |  |  | client email not shown in profile but there is email in database | High | 5 |  | 2017-03-01
125 | 11 |  | Client |  |  | visa requested, visa type missing in client profile but exist in database | High | 5 |  | 2017-03-01
126 | 11 |  | Client |  |  | Billing address and phone number need to include in client profile? | Low | 1 | KIV | 2017-03-01
127 | 11 |  | Client |  |  | Send screening email from client profile (eg compile 3 screenings into 1 email) | High | 5 |  | 2017-03-01
128 | 11 |  | Protect |  |  | Protect, after logout, still can access the page | High | 5 |  | 2017-03-01
129 | 11 |  | Page Redirection |  |  | aceess the edit screening page via url and redirect to view all screenings page | Low | 1 |  | 2017-03-01
130 | 11 |  | Page Redirection |  |  | aceess the clientinfo (individual client profile) via url and redirect to view all client page | Low | 1 |  | 2017-03-01

## Mitigation Plan
0 | Fix during buffer time
11 | Use planned debugging time in the iteration
21 | Stop current development immediately and resolve bugs. PM to reschedule the project