## Sheet1
Iteration 1 | Teh Kaixin | Chien Shuyan | Nicole Goh | Nabilah Banu | Sean Kwok |  |  | Iteration | Planned | Actual
meeting | 8 | 8 | 8 | 8 | 8 |  |  | 1 | 80 | 75
individual | 5 | 3 |  | 6 | 1.5 |  |  | 2 | 140 | 153.25
PM | [7 empty] | 3 | 45 | 55
BA |  |  |  | 4 |  |  |  | 6 | 90 | 111.25
CSV files | 4 |  |  | 4 |  |  |  | 7 | 150 | 155
Draft proposal | 1.5 | 1.5 | 1.5 | 1.5 | 1.5 | Planned: 80 |  | 8 | 150 | 170
total | 18.5 | 12.5 | 9.5 | 23.5 | 11 | 75 |  | 9 | 150 | 142
[8 empty] | 10 | 160 | 155
Iteration 2 | Teh Kaixin | Chien Shuyan | Nicole Goh | Nabilah Banu | Sean Kwok
meeting | 13.5 | 13.5 | 13.5 | 13.5 | 13.5
individual | 10.5 | 5 | 5 | 9.5 | 3
Coding hours |  |  | 6 |  | 6
PM | 2
Integration |  |  |  |  | 3
Test cases |  | 2.5
Testing |  | 6 |  | 2 | 1
BA |  |  |  | 2
User Testing 1 | 6 | 3.25 |  | 7.5 | 5.5 | Planned: 140
Total | 32 | 30.25 | 24.5 | 34.5 | 32 | 153.25
Iteration 3 | Teh Kaixin | Chien Shuyan | Nicole Goh | Nabilah Banu | Sean Kwok
meeting | 2 | 2 | 2 | 1 | 2
individual
Prototype | 5.5 |  | 5.5
Coding hours |  |  | 1 |  | 2
PM | 3
Integration |  |  | 1 |  | 1
Test cases |  | 4
Testing | 2 | 8 |  | 2 | 4
BA |  |  |  | 3
Testing (Acceptance) |  | 1.75 |  | 1.75 | 0.5 | Planned: 45
Total | 12.5 | 15.75 | 9.5 | 7.75 | 9.5 | 55
Iteration 6 | Teh Kaixin | Chien Shuyan | Nicole Goh | Nabilah Banu | Sean Kwok |  | Functions
meeting | 7 | 7 | 7 | 7 | 7 |  | Screenings
individual
Coding/Debug |  |  | 18 |  | 14
PM | 5
Integration |  |  | 7 | 7 | 7
Test cases |  | 5
Testing |  | 9
BA |  |  |  | 2.75
Coach |  | 0.5 | 0.5 |  | 0.5 | Planned: 90
Total | 12 | 21.5 | 32.5 | 16.75 | 28.5 | 111.25
Iteration 7 | Teh Kaixin | Chien Shuyan | Nicole Goh | Nabilah Banu | Sean Kwok |  | Functions
meeting | 15 | 15 | 15 | 15 | 15 |  | Data Management
individual |  |  |  | 18 | 18 |  | Client
Coding hours
PM | 5
Integration |  |  | 7 | 7 | 7
Test cases |  | 5
Testing |  | 10
BA |  |  |  | 3
Coach | [5 empty] | Planned: 150
Total | 20 | 30 | 22 | 43 | 40 | 155
Iteration 8 | Teh Kaixin | Chien Shuyan | Nicole Goh | Nabilah Banu | Sean Kwok |  | Function
meeting | 18 | 18 | 18 | 18 | 18 |  | KPI
individual | [6 empty] | Ranking
Coding hours |  |  | 15 | 15 | 15
PM/Prototype | 7
Integration |  |  | 3 | 3 | 3
Test cases |  | 6
Testing | 3 | 10
BA
Coach | [5 empty] | Planned: 150
Total | 28 | 34 | 36 | 36 | 36 | 170
Iteration 9 | Teh Kaixin | Chien Shuyan | Nicole Goh | Nabilah Banu | Sean Kwok |  | Function
meeting | 14 | 14 | 14 | 14 | 14 |  | Gender and age
individual | [6 empty] | Dashboard
Code/Debug |  |  | 13 | 13 | 13
PM/Prototype | 6
Integration |  |  | 2 | 2 | 2
Test cases | 2 | 5 |  | 2
Testing/UT | 3 | 9
BA
Coach | [5 empty] | Planned: 150
Total | 25 | 28 | 29 | 31 | 29 | 142
Iteration 10 | Teh Kaixin | Chien Shuyan | Nicole Goh | Nabilah Banu | Sean Kwok |  | Function
meeting | 15 | 15 | 14 | 14 | 14 |  | Index
individual | 6 | 6 | 6 | 6 | 6 |  | Email
Coding hours |  |  | 3 | 3 | 3
PM/Prototype | 7
Integration |  |  | 7 | 7 | 7
Test cases |  | 5
Testing/UT | 5 | 6
BA
Coach | [5 empty] | Planned: 150
Total | 33 | 32 | 30 | 30 | 30 | 155
Iteration 11 | Teh Kaixin | Chien Shuyan | Nicole Goh | Nabilah Banu | Sean Kwok |  | Midterms prep
meeting
individual
Coding hours
PM/Prototype
Integration
Test cases
Testing/UT
BA
Coach | [5 empty] | Planned: 160
Total | 0 | 0 | 0 | 0 | 0 | 0
Iteration 12 | Teh Kaixin | Chien Shuyan | Nicole Goh | Nabilah Banu | Sean Kwok
meeting
individual
Coding hours
PM/Prototype
Integration
Test cases
Testing/UT
BA
Coach | [5 empty] | Planned: 130
Total | 0 | 0 | 0 | 0 | 0 | 0
Iteration 13 | Teh Kaixin | Chien Shuyan | Nicole Goh | Nabilah Banu | Sean Kwok
meeting
individual
Coding hours
PM/Prototype
Integration
Test cases
Testing/UT
BA
Coach | [5 empty] | Planned: 130
Total | 0 | 0 | 0 | 0 | 0 | 0
Iteration 14 | Teh Kaixin | Chien Shuyan | Nicole Goh | Nabilah Banu | Sean Kwok
meeting
individual
Coding hours
PM/Prototype
Integration
Test cases
Testing/UT
BA
Coach | [5 empty] | Planned: 130
Total | 0 | 0 | 0 | 0 | 0 | 0