## Overall Bug Score
Iteration | Task | Test (Number of tests) | Low Impact Bugs | High Impact Bugs | Critical Bugs | Score | Actions Taken
2 | Analysis - Doctor | 4 | 3 | 1 | - | 8 | Fix during buffer time
| Analysis - Referral | 3 | 1 | 2 | - | 11 | Fix during planned debugging time
| Analysis - Specialty | 1 | 1 | - | - | 1 | Fix during buffer time
| KPI - Medical | 2 | - | 1 | - | 5 | Fix during buffer time
| Gender & Age Report | 1 | - | 1 | - | 5 | Fix during buffer time
| Total Score for Iteration 2 |  |  |  |  | 30 | Stop current development and resolve bugs

## Bug Log
S/N | Iter. | Function | Test No | Expected Result | Issues / Differing Result | Severity | Points | Status | Date Discovered | Date resolved | Remarks
1 | 2 | Analysis - Doctor | 1 | System should show result | No output | Low | 1 | unsolve | 2016-10-30
2 | 2 | Analysis - Doctor | 2 | System should show result | Wrong Output | High | 5 | unsolve | 2016-10-30
3 | 2 | Analysis - Doctor | 3 | System should show result | No output | Low | 1 | unsolve | 2016-10-30
4 | 2 | Analysis - Doctor | 4 | System should show result | No output | Low | 1 | unsolve | 2016-10-30
5 | 2 | Analysis - Referral | 1 | System should show result | Wrong Output | High | 5 | unsolve | 2016-10-30
6 | 2 | Analysis - Referral | 2 | System should show result | Wrong Output | High | 5 | unsolve | 2016-10-30
7 | 2 | Analysis - Referral | 3 | System should show result | No output | Low | 1 | unsolve | 2016-10-30
8 | 2 | Analysis - Specialty | 1 | System should show result | No output | Low | 1 | unsolve | 2016-10-30
9 | 2 | KPI - Medical | 1 | System should show result | Wrong Output | High | 5 | unsolve | 2016-10-30
10 | 2 | Gender and Age | 1 | System should show result | Wrong Output | High | 5 | unsolve | 2016-10-30