## Overall Bug Score
Iteration | Task | Test (Number of tests) | Low Impact Bugs | High Impact Bugs | Critical Bugs | Score | Actions Taken
|  |  | 1 | 5 | 10
2 | Analysis - Doctor | 0 | 0 | 0 | 0 | 0 | Fix during buffer time
| Analysis - Referral | 0 | 0 | 0 | 0 | 0 | Fix during planned debugging time
| Analysis - Specialty | 0 | 0 | 0 | 0 | 0 | Fix during buffer time
| KPI - Medical | 1 | 0 | 1 | 0 | 5 | Fix during buffer time
| Gender & Age Report | 1 | 0 | 1 | 0 | 5 | Fix during buffer time
| Client - Create | 0 | 0 | 0 | 0 | 0 | Fix during buffer time
| Screening - CRUD | 5 | 5 | 0 | 0 | 5 | Fix during buffer time
| Total Score for Iteration 2 |  |  |  |  | 15 | Use planned debugging time in the iteration

## Bug Log
S/N | Iter. | Function | Test No | Expected Result | Issues / Differing Result | Severity | Points | Status | Date Discovered | Date resolved | Remarks
1 | 2 | Analysis - Doctor | 1 | System should show result | No output | Low | 1 | solved | 2016-10-30 | 2016-10-31
2 | 2 | Analysis - Doctor | 2 | System should show result | Wrong Output | High | 5 | solved | 2016-10-30 | 2016-10-31
3 | 2 | Analysis - Doctor | 3 | System should show result | No output | Low | 1 | solved | 2016-10-30 | 2016-10-31
4 | 2 | Analysis - Referral | 1 | System should show result | Wrong Output | High | 5 | solved | 2016-10-30 | 2016-10-31
5 | 2 | Analysis - Referral | 2 | System should show result | Wrong Output | High | 5 | solved | 2016-10-30 | 2016-10-31
6 | 2 | Analysis - Referral | 3 | System should show result | No output | Low | 1 | solved | 2016-10-30 | 2016-10-31
7 | 2 | Analysis - Specialty | 1 | System should show result | No output | Low | 1 | solved | 2016-10-30 | 2016-10-31
8 | 2 | KPI - Medical | 1 | System should show result | Wrong Output | High | 5 | unsolve | 2016-10-30
9 | 2 | Gender and Age | 1 | System should show result | Wrong Output - output in wrong age category | High | 5 | unsolve | 2016-10-30
10 | 2 | Client - Create | 1 | System should show success result | No output | Low | 1 | solved | 2016-10-30 | 2016-11-01
11 | 2 | Client - Create | 2 | System should show success result | No output | Low | 1 | solved | 2016-10-30 | 2016-11-01
12 | 2 | Screening - CRUD (Type Male & Female) | 1 | System should show success result / redirect back to screening page | Unable to add / no display | Low | 1 | solved | 2016-10-30 | 2016-11-03
13 | 2 | Screening - CRUD (Type Male) | 2 | System should show success result / redirect back to screening page | Unable to add / no display | Low | 1 | solved | 2016-10-30 | 2016-11-03
14 | 2 | Screening - CRUD (Type Female) | 3 | System should show success result / redirect back to screening page | Unable to add / no display | Low | 1 | solved | 2016-10-30 | 2016-11-03
15 | 2 | Screening - CRUD (Type Infant) | 4 | System should show success result / redirect back to screening page | Unable to add / no display | Low | 1 | solved | 2016-10-30 | 2016-11-03
16 | 2 | Screening - CRUD | 5 | System should show success result / redirect back to screening page | Unable to edit any screenings | Low | 1 | unsolve | 2016-10-30

## Mitigation Plan
0 | Fix during buffer time
11 | Use planned debugging time in the iteration
21 | Stop current development immediately and resolve bugs. PM to reschedule the project