## Overall Bug Score
Iteration | Task | Test (Number of tests) | Low Impact Bugs | High Impact Bugs | Critical Bugs | Score | Actions Taken
|  |  | 1 | 5 | 10
2 | Analysis - Doctor | 3 | 0 | 0 | 0 | 0 | -
| Analysis - Referral | 3 | 0 | 0 | 0 | 0 | -
| Analysis - Specialty | 3 | 0 | 0 | 0 | 0 | -
| KPI - VISA | 3 |  |  |  |  | -
| KPI - Medical | 2 | 0 |  | 0 | 0 | -
| Gender & Age Report | 1 | 0 |  | 0 | 0 | -
| Client - CRUD | 3 | 0 | 1 | 0 | 5 | Fix during buffer time
| Screening - CRUD | 6 |  | 1 | 0 | 5 | Fix during buffer time
| Total Score for Iteration 2 |  |  |  |  | 10 | Fix during buffer time
3 | Login | 12 | - | 3 | - | 15 | Use planned debugging time during iteration
| Account Management | 8 | 4 | 1 | - | 9 | Fix during buffer time
| Protect | 7 | - | 3 | - | 15 | Use planned debugging time during iteration
| Total Score for Iteration 3 |  |  |  |  | 39
6 | Screenings | 15 | 4 | 3 |  | 19 | Use planned debugging time during iteration
| Total Score for Iteration 6 |  |  |  |  | 19

## Bug Log
S/N | Iter. | Function | Test No | Expected Result | Issues / Differing Result | Severity | Points | Status | Date Discovered | Date resolved | Remarks
1 | 2 | Client - Edit | 2 | System should show the updated info for client | Unable to edit any client | High | 5 | unsolved | 2016-10-30 | - | Function dropped
2 | 2 | Screening - Edit | 5 | System should show the updated info for screening | Unable to edit any screenings | High | 5 | unsolved | 2016-10-30 | - | Pushed to future iteration due to rescope
3 | 3 | Login & Account Management - login | 1,5,8 | Error Message Shown for wrong credentials | No error message, not sure is UI not display properly or codes did not do validation for wrong credentials | High | 5 | solved
4 | 3 | Login & Account Management -acct | 7 | Account created or related message should show | Username is taken was shown instead of account created and it appeared for 1 second | Low | 1 | solved
5 | 3 | Login & Account Management -acct | 11,22 | Able to change user/admin's password | Page did not respond when clicking the reset button, browser then appear out of memory | High | 5 | solved | 2017-07-01
6 | 3 | Login & Account Management - login | 12 | Error Message Shown for wrong credentials | able to login with old password, ecf from test no 11 | High | 5 | solved | 2017-07-01
7 | 3 | Login & Account Management - login | 13 | Redirect to homepage | Unable to log in with the updated password, ecf from test no 11 | High | 5 | solved
8 | 3 | Login & Account Management -acct | 14 | Account deleted or related message should show | Did not show success message | Low | 1 | solved
9 | 3 | Login & Account Management -acct | 15,16 | Account created or related message should show | page did not redirect / refresh. Have to manually go to acct management page to see it work. | Low | 1 | solved | 2017-07-01
10 | 3 | Login & Account Management -protect | 18 | Normal user should not able to access the page | able to access the url and did not redirect to home page or show error message | High | 5 |  | 2017-07-01
11 | 3 | Login & Account Management -protect | 19 | Normal user should not have the acct management tab in their header | able to access the url and did not redirect to home page or show error message | High | 5
12 | 3 | Login & Account Management -acct | 20, 21 | Error Message shown for account existed | Error message shown for one second but disappear after that. | Low | 1 | solved
13 | 3 | Login & Account Management -protect | 23,24,25,26 | Unable to access the page without login | Able to access | High | 5 | Solved
| 3 | Login & Account Management -acct | 27 | Normal user should not able to access the page | able to access edituserpassword and createaccount.html, tried to create an account and account created message shown but db did not capture it | High | 5 |  | 2017-07-01
14 | 3 | Login & Account Management - value validation | 28 | input empty fields should display when clicking the reset password | Nothing happens | Low | 1 | solved | 2017-08-01
15 | 6 | Screenings - C | 1,2,3,4 | Add Screenings | page refreshed when clicking the add button, but screenings was not added to db. | High | 5 | Solved
16 | 6 | Screenings - R | 7 | Success message should show to indicate screenings updated | no success message | Low | 1 | Solved
17 | 6 | Screenings - U | 6 | Able to edit screening (edit those that created in test1,2,3,4) | No screenings in the view screening page, unable to edit | Low | 1 | Solved
18 | 6 | Screenings - D | 8 | Able to click on the delete button, screening removed from db | Demograhics affected was updated wrongly | High | 5 | Solved | 2017-08-01
19 | 6 | Screenings - value specific validation | 10,11 | Infant's Age validation for add screening | No error message shown (UI), screenings was added | High | 5 | Solved
20 | 6 | Screenings - Filter |  | Able to filter screenings for infant between 0 to 2 years old | Filter missing | Low |  |  | 2017-08-01 |  | Feature dropped
21 | 6 | Screenings - Filter |  | Display screenings' details according to the filter | Filter missing | High |  |  |  |  | Feature dropped
22 | 6 | Screenings - Client List |  | View filtered screening's client list | Filter missing | High |  |  |  |  | Feature dropped
23 | 6 | Screenings - sort | 23-27 | Display result in a sorted order (asc - desc / desc - asc) | Unable to click on the header to sort | Low | 1 | Solved | 2017-08-01
24 | 6 | Screenings - value validation | 30 | Error message to show "input empty fields" | Filter missing, therefore unable to click on generate button | High | 5 | Solved | 2017-08-01
|  | Added By KX |  | BUG description
25 |  | Login & Account Management |  | Clicking on "Edit" even when password is empty | Success msg is still shown BUT should display error msg |  |  | solved
26 |  | Login & Account Management |  | login with new password | Cannot log in with new password |  |  | solved
27 |  |  |  |  | Username is taken displayed even though new |  |  | solved
28 |  | Screenings |  | No success msg to show added screenings |  |  |  | solved
29 |  |  |  | Add female/male/infant only but all 3 come out |  |  |  | solved |  |  | Intended to be this way
30 |  |  |  | Empty field error msg shown at wrong field |  |  |  | solved
31 |  | Edit screenings |  | Fields not autopopulated for screening |  |  |  | solved
32 |  |  |  | When all fields entered, old screening edit, new screening also created |  |  |  | solved
33 | 7 | Upload - wrong file format | 1,2,3,4 | Error with file or related message should show, timestamp should not be updated | page redirect with no error / success message | Low | 1
34 | 7 | Upload - wrong header structure, file correct format | 5 | Wrong File format shown Content should not be found in database Timestamp should not be updated | page redirect with no error / success message | Hgh | 5
35 | 7 | Upload - correct file format | 6 | "File successfully updated" shown 100 Records loaded into database Timestamp updated to current time | page redirect with no error / success message | High | 5
36 | 7 | Upload - csv file | 7 | "Wrong File Format" shown Timestamp should not be updated to current time | page redirect with no error / success message | High | 5
37 | 7 | Upload - correct file format | 8 | "File successfully updated" shown 300 Records loaded into database Timestamp updated to current time | page redirect with no error / success message | High | 5
38 | 7 | Upload - correct file format | 9 | "File successfully updated" shown 400 Records loaded into database Timestamp updated to current time | page redirect with no error / success message | High | 5
39 | 7 | Upload - correct file format | 10 | "File successfully updated" shown 1000 Records loaded into database Row 2003 - 2005 should not be found in database Timestamp updated to current time | page redirect with no error / success message | High | 5
40 | 7 | Upload - correct file format | 11 | "File successfully updated" shown 700 Records loaded into database Row 703 - 705 should not be found in database Timestamp updated to current time | page redirect with no error / success message | High | 5
41 | 7 | Upload - correct file format | not in testcase | Upload Testing2.1 "File successfully updated" shown 200 records loaded into db, timestamp updated to current time | page redirect with no error / success message | High | 5
42 | 7 | Upload - correct file format, wrong header | 12 | Data not relevant or related message shown | page redirect with no error / success message |  |  |  |  | 2017-01-22
43 | 7 | Clients Page - Sort Client | 1 - 6 | Sort Clients in an order | No cients displayed | High | 5 | solved
44 | 7 | Client - Display Profile | 7,9 | Display Client's profile | Unable to click on client's name to view its profile | High | 5 | solved |  | 2017-01-22
45 | 7 | Client - Display Profile | 8,10 | View Client's appointments | Unable to view | High | 5 | solved |  | 2017-01-22
46 | 6 | Screenings - Add (Adults) | - | in viewScreeningsAdult.html, upon clicking 'add new screening' , it should redirect to addscreeningadult.html | direct to addscreening.html (for infant) | low |  | solved |  | 2017-01-22
47 | 6 | Screenings - Add (Infant) |  | Vaccination / Screening | Vaccination/ screening | low | 1
48 | 6 | Screenings - Link to Patient View |  | Should display male clients above 20 years old for Cancers | Returned Client A, C,D,E,F whose gender are either male / female / blank | High | 5
49 | 6 | Screenings - Link to Patient View |  | Should display infant for illness - pwqpqpw | Returned Client A, C,D,E,F, G whose age are above 6 | High | 5
50 | 6 | Screenings - sort adult |  |  | Gender = Male, the whole table shrink in size | High | 5 | solved |  | 2017-01-22
51 | 6 | Screenings - sort adult |  |  | After sorting gender = male, sort back to 'all', there is no change in result | High | 5 | solved |  | 2017-01-22
52 | 6 | Screenings - sort adult |  |  | After sorting gender = male, sort back to female and the table disappear, 'delete' was shown | High | 5 | solved |  | 2017-01-22
53 | 6 | Screenings - sort infant |  |  | when sorting the age, illness and screening for infant, the data for infant changes to adult's | High | 5 | solved |  | 2017-01-22
54 | 7 | Upload - timestamp |  |  | timestamp updated to current time, last three lines of the data file were also uploaded into database | High | 5
55 | 7 | Client List - drop down list |  | Table should show data based on the dropdown list | No change in table - data not sorted | High | 5 | solved |  | 2017-01-22
56 | 7 | View Client Info |  | Should show the various screenings for each client | No screenings shown in each client info | High | 5 | solved |  | 2017-01-22
57 |  | Seach Box in Navigator |  | Shouldn’t show in the header for all pages |  | High | 5 | solved |  | 2017-01-22
58 | 7 | Screenings - sort adult |  | gender = male , currently display both male and female | Gender = male , display screenings for male. | Low | 1 |  | 2017-01-22
59 | 7 | Screenings - Sort Adullt (Result Sequence) |  | common illness and screening not sorted in correct order |  | High | 5 |  | 2017-01-22
60 | 6 | Search in Screening |  | searched 'check' should appear screenings with 'check %' (linda's request) | displayed both 'check %' and '% check %' | High | 5 |  | 2017-01-22
60 | 7 | Search in client |  | searched 'di' should appear clients with 'di' as starting name (Linda's request) |  | High | 5 |  | 2017-01-22
60 | 8 | Report - KPI |  | No response when clicking the generatte results button | Should display result | High | 5 |  | 2017-01-22

## Mitigation Plan
0 | Fix during buffer time
11 | Use planned debugging time in the iteration
21 | Stop current development immediately and resolve bugs. PM to reschedule the project